## ProviderList
VendorCode | Name | Status | GoLiveDate | ProjectManager | Phase | Fees | Type | Update
HS001 | Henry Schein | Live | March | Martha | Testing | Waived for SBI | FMO | Test work orders and script samples provided 2/23/20. Henry Schein advised that they are targeting some UAT testing the week of 2/24.
BV001 | Brightview | Live | March | Martha | Testing | $12,000.00 | FMO | White listing and tokens issued 1/6/20. API L1 Help Desk providing support. Call scheduled for 2/25/20 to discuss API use with Home Depot.
PT001 | Paintzen | On Boarding | 02/28/2020 | Martha | QA Certification | $12,000.00 | IFM | Provider passed QA prep, QA certification call scheduled for 2/27/20.
PC001 | PC Maintenance/Smartsheet | Live | 02/27/2020 | Martha | QA Certification | Waive Cost for HD | FMO | Provider attempted QA certification 2/19/20 but API call resulted in duplicate work orders in vendor Smartsheet. QA Certification re-scheduled for 2/28/20.
PB001 | PTR Baler | Staging Whitelisted | TBD | Martha | Testing | $12,000.00 | FMO/IFM | Provider has been white listed and testing token provided Jan 24th. Help desk has been providing test work orders.
AF001 | Academy Fire | On Boarding | TBD | Martha | Planning | TBD | IFM | Attended kick off meeting Jan 21st. Links to API vendor support web page and connector manual provided. Provider declined STPL developer option.
MX001 | MaintenX | On Boarding | TBD | Martha | Planning | Waived | FMO | Agreements signed 1/23. Fees waived per Josh. QA testing requirements provided. Maintenx sent response to follow up email stating that they are still in planning stages and not yet ready for testing.
CP001 | Century Fire protection | Live | TBD | Martha | Planning | $12,000.00 | IFM | Agreements sent to provide Jan 29th. Provider also sent link to register for weekly provider kick off call along with presentation deck.
NX001 | Nixon | Staging Whitelisted | TBD | Martha | Testing | Waived | FMO/IFM | Nixon attended kick off call 11/14/19 and is now adding Home Depot, Office Depot and Davita.
PX001 | Phoenix Technologies | Live | TBD | Martha | Testing | $12,000.00 | FMO | 2/10 provider will be testing with Office Depot. They have not specifically asked for any test work orders at this time.
TG001 | Telgian | Live | Ph 2 - In process | Martha | Testing Quotes | $12,000.00 | FMO | The provider went live in January with phase 1.They are currently adding the quote feature to their API. A bug fix is being released in production on 2/26 so that they can roll their quote API into production.
PK001 | Park Construction | On Boarding | TBD | Martha | Planning | Waived | FMO | 2/25 in process to white list and issue a token for Home Depot and Davita.
NA001 | NA | On Boarding | TBD | Martha | QA Certification | Waived | FMO UPS | High priority provider, pending information on move of all UPS vendors to SI7
PC002 | Park Construction | On Boarding | TBD | Martha | White Listing | Waived | FMO UPS | High priority provider,
TS001 | Test | New | April | Irfan | New | Waived | New | test change
AB001 | New123 | Live | April | Martha | QA Certification | Waived | New | New
NE001 | Check | New | June | Martha | Testing | Waived | FMO | Check
NN012 | test provider | Live | June | Martha | White Listing | TBD | IFM | chech provider date

## IssueList
VendorCode | Name | Item | Issue | Owner
TG001 | Telgian | 1 | Quote bug fix required in FmPilot- QA testing being completed and added to branch | Lordell
PK001 | Park Construction | 1 | Need confirmation that provder is approved to do business with Davita | Josh Casto
PK001 | Park Construction | 2 | Need AC repair | Test Owner
TS001 | Test | 1 | Test issue | Irfan